CBSE Sahodaya Digital Platform

Master Pending Work Plan

Generated 2026-07-13 · Covers all 21 FRDs · Consolidates the FRD-08 build plan, the Sports Event Head residual gap, and the deferred FRD-19/FRD-20 scope

# 1. Executive Summary

Of the 21 functional requirement documents covering this platform, 18 are fully implemented, verified, and committed — including every module re-audited more than once this program (Sports, Finance, Security, Multi-Tenant Platform, Reporting, Workflow, Documents, Notifications, Shared Masters, Platform Services, DevOps). Three items remain open, in three different senses:

☐  FRD-08 Custom Competition Management — genuinely not started. This is a real multi-week build (a low-code competition builder), not a hardening pass. Full 9-phase plan in §2.

☐  FRD-04 Sports — done, with one small residual gap found in this session’s re-survey: the new "Sports hub" / Event-Head-promotion feature is half-wired (service + status display exist, but the actual hub page and promote action do not). Detail in §3.

☐  FRD-19 Public Portal and FRD-20 Website Builder/CMS — both have real, sizeable gaps (documented in earlier audits), but you’ve explicitly deferred both. Kept here only as a reference so the gaps aren’t forgotten; no action planned unless you ask. See §4.

A short list of items were explicitly descoped by you rather than left incomplete — see §5.

# 2. Status by FRD

| FRD | Module | Status |
| --- | --- | --- |
| FRD-01 | Sahodaya Setup & School Membership | Done |
| FRD-02 | Student & Teacher Registry | Done |
| FRD-03 | Competition Engine Core Framework | Done |
| FRD-04 | Sports Management | Done (1 residual gap — see §3) |
| FRD-05 | Kalotsav Management | Done |
| FRD-06 | Finance & Accounts | Done |
| FRD-07 | Examination Management (MCQ/Talent Search) | Done |
| FRD-08 | Custom Competition Management (low-code builder) | Pending — full build, see §2 |
| FRD-09 | Teacher Training & Professional Development | Done |
| FRD-10 | Workflow & Approval Engine | Done |
| FRD-11 | Document & Template Engine | Done |
| FRD-12 | Notification & Communication Engine | Done |
| FRD-13 | Super Admin & Multi-Tenant Platform | Done |
| FRD-14 | Reporting, Analytics & BI Engine | Done |
| FRD-15 | Security, Audit & Access Control | Done |
| FRD-16 | Shared Masters & Configuration Engine | Done |
| FRD-17 | Platform Services & Common Utilities | Done |
| FRD-18 | Deployment, DevOps & Infrastructure | Done |
| FRD-19 | Public Portal, Live Results & Public Info | Deferred by client — see §4 |
| FRD-20 | Multi-Site Website Builder / CMS | Deferred by client — see §4 |
| FRD-21 | CBSE Academic Results, Toppers & Achievements | Done |

# 3. FRD-08 — Custom Competition Management (the one real gap)

Coverage today: ~18%. What exists is a well-built but hardcoded per-type engine — every new competition category requires a developer to touch validation whitelists, catalog mappings, and a fixed programs list. The FRD asks for a true low-code builder: an admin defines a brand-new competition type (e.g. "Robotics", "Debate") with its own Areas, eligibility rules, fee schedule, tie-break logic, notifications, and reports — zero developer involvement.

The strongest existing foundation is FestTaxonomyMaster (tenant-scoped, admin-editable dimension master) and the already-generic FestEventItem table — this plan builds outward from that rather than starting over.

## Phase breakdown

| # | Phase | Delivers | Depends on | Effort |
| --- | --- | --- | --- | --- |
| 0 | Foundations & Masters | Competition Type master table + admin CRUD; item-category taxonomy moved off the hardcoded enum onto FestTaxonomyMaster. | None | 8–12d |
| 1 | Competition Builder wizard | Admin creates a brand-new competition type (e.g. "Robotics") — name/code/year/dates/levels — with zero code changes. | Phase 0 | 10–15d |
| 2 | Area Builder | New competition_areas entity (distinct from FestItemHead) — unlimited sub-areas per competition with their own registration rules/fees. | Phase 1 | 12–18d |
| 3 | Eligibility Builder | Data-driven eligibility rules (Student/Teacher/Class/Subject/School/Region/Custom) replacing hardcoded PHP conditionals. | Phase 0–1 | 15–20d |
| 4 | Item Builder generalization | Explicit Pair/Trio participant types, Result Method field, category taxonomy wired into the item form. | Phase 0 | 5–8d |
| 5 | Qualification / tie-break rules | Configurable tie-break/lot-draw logic beyond today’s plain top-N cutoff. | Independent | 8–10d |
| 6 | Notification template generalization | Generic per-competition-type notification mapping (Payment Pending, Registration Open, Competition Reminder, Certificate Available). | Phase 1 | 6–8d |
| 7 | Reporting extension | Area-wise reports; confirm item-wise/school-summary reports already generalize for custom types. | Phase 2 | 8–10d |
| 8 | Migration, backfill & regression | Seed Competition Type rows for the 6 existing hardcoded types; repoint validation/catalogs at the new masters; full regression across all live event types. | Phases 0–7 | 10–15d |

Total estimated effort: ~82–116 person-days across all 9 phases.

## Recommended first milestone

Phases 0, 1, and 4 (~23–35 person-days) deliver the single most FRD-visible outcome — an admin can add "Robotics" as a real competition type with its own item categories, with zero code changes — without committing to the larger Area/Eligibility phases yet. Phases 2, 3, 5, 6, 7 can each be scoped and greenlit independently once Phase 1 is live. Phase 8 (migration/regression) must run at the end of whichever phases are actually built — it is the highest-risk phase since it repoints validation used by the 6 competition types already live in production.

## Descoped from the FRD-08 build

A fully generic, cross-domain Workflow/Approval Engine (shared by Fest, MCQ, Membership, Training, Board Results) was flagged as architecturally desirable but not urgent — each domain’s hand-rolled state machine was independently verified to have correct guards. Building Areas/Eligibility on top of a not-yet-existing generic engine would mean building two large things at once, so each domain keeps its own explicit status logic for now.

# 3a. FRD-04 Sports — residual gap found in this session

The Event Head redesign from the last working session is now in good shape: fees/policy are captured at head-creation time, the setup checklist correctly detects the new composite fee columns, duplicate navigation on the Competition page is gone, and a shared fee-fields component keeps the Add-Head form consistent. Re-checking the flow end to end surfaced one new, concrete gap introduced by the newest layer of work (the "promote heads into independent discipline events" feature):

☐  Sports hub page is missing. Both the Add-Head banner and the Competition page link to a "Sports hub" (/sahodaya-admin/{tenant}/sports) to actually run the promotion — no route or Vue page exists for it today. Clicking either link 404s.

☐  No endpoint to execute the promotion. PromoteSportsHeadsToDisciplineEvents::promote() exists and is fully implemented, but nothing in routes/web.php calls it — only ->status() is wired in, to compute the "N heads ready to promote" banner text.

☐  Minor: the standalone ItemHeads.vue page still hand-duplicates the fee-field markup instead of reusing the shared FestHeadFeeFields component used elsewhere. Not a bug today (fields match), but a future field change would need updating in two places.

You already asked for the Sports hub to be built; that build is the natural next implementation step once this plan is reviewed — estimated at 1–2 days (list view of season events + pending-heads count, a promote button per event, and the POST route wired to the existing service).

# 4. Deferred by you — reference only, no action planned

These two are kept here so the known gaps aren’t lost, not because they’re next in line. Nothing in this section will be built unless you ask for it.

## FRD-19 — Public Portal, Live Results & Public Information

Coverage: 41% · 5 Critical / 9 Major / 8 Minor issues · est. 95–125 person-days

The festival results portal itself is genuinely strong (real privacy-gating, working 30-second live polling). What’s missing is the broader public surface: no public school directory, no public Topper/Achievement/BoardResult pages (models exist and are admin-managed, but never rendered publicly except as manually-typed CMS JSON), no Public API layer (Results/Points/School/Stats/Verification), no real analytics beyond a single visitor counter, and no true push/WebSocket delivery (the Echo code in Scoreboard.vue is dead — broadcasting is log-driver only). One functional bug worth flagging even though the FRD is deferred: SetPublicCacheHeaders applies a blanket 1-hour public Cache-Control to every public GET, including the live-results polling endpoint, which can make live scores appear stale behind a caching layer.

## FRD-20 — Multi-Site Website Builder / CMS

Coverage: 46% · 5 Critical / 9 Major / 8 Minor issues · est. 145–185 person-days

The section-based CMS is real and substantial (41 section types, 108 layout variants, skin/theme system). Against the FRD’s full "multi-site builder" vision it’s short on: draft/publish/version-history/rollback (edits go live instantly, no staging), true multi-site-per-account (hard 1 tenant = 1 website), self-service custom domains (the domains table/resolver exist but there’s no CMS-facing "add my domain" screen), a generic Forms Builder, page-level SEO/OG/schema markup, and CMS role granularity (Editor/Reviewer/Publisher don’t exist — access is binary). One security item worth flagging regardless of deferral: the WYSIWYG field renders as a plain textarea with content echoed via Blade’s raw {!! !!} in 21 section partials with zero sanitization — a stored-XSS risk if a lower-trust editor role is ever introduced.

# 5. Explicitly descoped (not gaps — deliberate scope decisions)

These were raised during the Student/Teacher Registry work and explicitly excluded by you (“not our purpose” / “dont need section for students”). Not reopened unless you ask:

•  TC / Transfer Certificate workflow

•  Student class-promotion / academic-year rollover engine

•  Division/Section field on Student

# 6. Suggested order of work

- Build the Sports hub page + promote route (1–2 days) — small, closes out the one loose end from the last session, unblocks a feature you already asked for.

- FRD-08 Phase 0 (Foundations & Masters) (8–12 days) — everything else in FRD-08 depends on this; on its own it also fixes the two-source-of-truth item-category enum problem.

- FRD-08 Phases 1 and 4 (15–23 days) — completes the "recommended first milestone": a real no-code competition type with its own item categories.

- Decide on FRD-08 Phases 2/3/5/6/7 once Phase 1 is live and there’s a real second competition type to build it against — each phase is independently scoped and can be greenlit on its own.

- Revisit FRD-19 / FRD-20 only when you’re ready — both are large (95–185 person-days combined) and independent of the above.