# Multi-Web Remaining Work — Detailed Task List

CBSE Sahodaya Digital Platform · Generated 2026-07-11 · Task IDs match the in-app task tracker (#76-157)

64 remaining actionable tasks across 3 modules (of an original 82 tracked; 18 are now done or descoped — see note below). Sports Management and Teacher Registry (both sides, including Student Registry) are fully done and not included. Talent Search's Critical exam-integrity tier is also done — only its High/Medium/Low items remain below. Teacher Training's Critical tier (7 tasks) is now done — only its High/Medium/Low items remain below. TC/Transfer Certificate workflow, student class-promotion/rollover, and the Division/Section field are excluded per the client's scope decisions ("not our purpose" / "dont need section for students").

# Done — Student Registry (FRD-02, student side)

All 10 remaining tasks (#76-77, #79-86) found already implemented in the working tree and committed: reject-with-remarks + bulk reject, all 4 FRD notification triggers, dead-method cleanup, CSV duplicate-check, TC report gating, SoftDeletes, roster CSV/XLSX/PDF export, fest/sports controller split, composite DB index. #78 (Division/Section field) remains Descoped per client scope decision.

# Teacher Training (FRD-09) — 19 tasks, ~44-54 pd

QR registration/attendance and the Critical tier (pending-school resolution, report-filter fixes, attendance-based certificate eligibility, feedback module, bulk registration/CSV, CPD tracking, eligibility builder) are done and committed. Remaining work concentrates in Resource Person management, differentiated fees, category master, and multi-type certificates.

| # | Tier | Task | Effort |
| --- | --- | --- | --- |
| 94 | High | Resource Person/Trainer management New resource_persons table + pivot with honorarium; Sahodaya master screen; fix RPT-TRN-012 (currently fabricates names). | 6d |
| 95 | High | Differentiated school-fee vs teacher-fee Wire the existing but dead TrainingSchoolFee table into a real school-level invoice/approve flow. | 6d |
| 96 | High | Training category master New training_categories table/enum; category column + builder dropdown + Index filter. | 3d |
| 97 | High | Multi-type certificates Completion/Appreciation/Resource-Person/Organizer templates via CertificateTemplate.certificate_type; print training hours. | 5d |
| 98 | High | Missing notifications Payment Reminder, Training Reminder, Daily Session Reminder, Certificate Available. | 4d |
| 99 | High | Existing-teacher profile refresh on QR re-registration Update photo/DOB/gender/designation/experience on a matched existing Teacher instead of discarding submitted data. | 1d |
| 100 | Medium | Waiting list Capacity limit, waitlist position, promotion on freed seat, waitlist notification. | 5d |
| 101 | Medium | Program code + banner image code, banner_image_path columns + builder fields + upload widget. | 2d |
| 102 | Medium | Invoice generation step Persisted invoice record/PDF between Registration and Payment. | 4d |
| 103 | Medium | Training ID Card Reuse the existing Fest ID-card pattern; new stage between Approval and Attendance. | 5d |
| 104 | Medium | Late/With-Permission attendance states + correction-approval Extend attendance status enum; correction_reason/corrected_by/approval_status; marked_by FK; approval UI. | 5d |
| 105 | Medium | Teacher-Type/Subject/Day-wise participation reports 3 new report entries in ReportRegistry. | 2.5d |
| 106 | Medium | Session edit/delete routes TrainingSession currently has no update/destroy route. | 1d |
| 107 | Medium | Standalone Teacher-creation report view Split out of the QR dashboard counter into its own list with verification status. | 0.5d |
| 108 | Low | Fuzzy name-based duplicate detection Levenshtein/soundex threshold in TrainingPublicRegistrationService::findExistingTeacher(). | 1d |
| 109 | Low | De-duplicate QR download helpers downloadQr/downloadSessionAttendanceQr share a helper — maintainability only. | 0.5d |
| 110 | Low | Audit log on storeSession() Plain session creation still unaudited unlike QR/school-attendance actions. | 0.25d |
| 111 | Low | Per-program "allow school nomination" toggle Separate from the existing self-registration toggle. | 1.5d |
| 112 | Low | Verify no bypass path in updateAttendance() gate Registration-approval gate hardening — largely covered already, verify no remaining bypass. | 0.5d |

# Talent Search / MCQ Exams (FRD-07) — 15 tasks, ~25-36 pd

Critical tier (malpractice/withheld states, mark-edit guard, attendance-correction workflow, late-fee schema fix) is already done and committed.

| # | Tier | Task | Effort |
| --- | --- | --- | --- |
| 113 | High | Teacher exam registration path McqRegistration.teacher_id exists but unused. Extend eligibility for teacher-based rules; build registration screen (bulk + portal). | 5-6d |
| 114 | Medium | Result Analysis report Pass/fail rate, mean score, percentile distribution, grade histogram. | 2-3d |
| 115 | Medium | School-wise Performance report Aggregate average score/pass-rate/rank-distribution across schools for an exam. | 2-3d |
| 116 | Medium | Malpractice Register report New export in McqReportService now that malpractice/withheld attendance states exist. | 1d |
| 117 | Medium | Wire rank_eligible into ranking service McqRankingService::rankExam() currently ignores rank_eligible — non-rank-eligible bands still get ranked. | 1d |
| 118 | Medium | Exam Reminder notification Scheduled command before scheduled_at; new mcq.exam.reminder template. | 1-2d |
| 119 | Medium | Certificate-ready notification McqCertificateService::issue()/issueBulk() never notify students. | 0.5-1d |
| 120 | Medium | Seat/hall auto-allocation seat_no is currently never populated; build seating-plan UI + allocation logic. | 3-4d |
| 121 | Low | Exam-code field Add code column to mcq_exams, expose in exam builder. | 0.5d |
| 122 | Low | Explicit registration-open/close + result-date fields registration_opens_at/closes_at, result_date + auto status-transition job. | 2d |
| 123 | Low | Per-student printable invoice Currently only a batch-total exists. | 1-2d |
| 124 | Low | Attendance/Mark/Result Sheet printable documents Only hall tickets and certificates have print templates today. | 2-3d |
| 125 | Low | Excel import for marks/attendance Reuse the SpreadsheetReader already built for student import. | 1d |
| 126 | Low | Public certificate verification page verification_uuid exists but no public /verify/{uuid} route/page. | 1-2d |
| 127 | Low | Negative marking / per-question weighting McqExamSessionService::submit() computes score unconditionally — relevant for Olympiad-style exams. | 2-3d |

# Academic Results, Toppers & Achievements (FRD-21) — 30 tasks, ~114-120 pd

Still a bare CMS content widget with zero workflow state and zero ranking logic — the largest remaining rebuild in the program.

| # | Tier | Task | Effort |
| --- | --- | --- | --- |
| 128 | Critical | Examination type + fix uniqueness key Add examination_type enum (AISSE/AISSCE); fix unique(tenant_id, class, examination_type, academic_year). | 2d |
| 129 | Critical | Add missing summary fields highest_mark, average_mark, remarks on board_results + validation + form. | 1d |
| 130 | Critical | Admission No / Roll No on Topper admission_no, roll_no columns + validateTopper() + Toppers.vue form fields. | 1d |
| 131 | Critical | PDF upload + version history result_pdf_path/attachment_paths + board_result_uploads table; enforce PDF present before Submit. | 6d |
| 132 | Critical | Verification/Approval/Publish workflow Reuse SchoolDocument approve/reject pattern; new BoardResultVerificationController + Verification.vue + routes. | 10d |
| 133 | Critical | Gate public sections on published status Filter stats-plus-toppers/toppers-cards/year-tabs Blade partials on status='published'. | 1d |
| 134 | Critical | Automatic Ranking Engine New RankingEngine + board_result_rankings (overall/stream/subject/pass-%/topper-count, tie-handling). | 12d |
| 135 | Critical | Sahodaya Dashboard for results Top schools, pending-verification count, recent awards, pass-% trend. | 5d |
| 136 | High | Configurable Top-N toppers topper_count_configs per Sahodaya; enforce cap server-side (currently unlimited). | 4d |
| 137 | High | Real Stream master exam_streams table replacing hardcoded BoardExamSubjects list; stream_id FK on toppers. | 3d |
| 138 | High | Subject-wise topper normalization topper_subject_marks table (reusing Subject model) replacing subject_marks JSON blob. | 6d |
| 139 | High | Academic Year FK academic_year_id FK (reusing AcademicYearRecord); backfill command; read-only lock on closed years. | 3d |
| 140 | High | Academic Performance Index engine Configurable weights (api_configs) + academic_performance_scores; recompute on publish. | 8d |
| 141 | High | Awards Engine (7 categories) academic_awards table + AwardsEngine service, auto-computed after Ranking + API engines run. | 8d |
| 142 | High | School Dashboard rank/topper widget Extend SchoolAdmin\DashboardController to read rankings/awards; new widget. | 3d |
| 143 | High | Public Portal upgrade Sahodaya-wide rankings, year selector, cross-school search, downloadable merit-list PDFs. | 8d |
| 144 | High | Merit Register + 5 core reports School Result Summary, Overall Ranking, Pass % Report, Class X + Stream Merit Registers. | 6d |
| 145 | High | 6 FRD notifications upload_reminder, submission_confirmation, verification_pending, result_approved/rejected/published. | 3d |
| 146 | High | Audit trail wiring DataChangeLogger calls on every BoardResult/Topper/Achievement mutation + Audit History tab. | 3d |
| 147 | Medium | Subject-wise Merit Register report Depends on subject normalization item above. | 2d |
| 148 | Medium | Academic Excellence Report + Historical Comparison Depends on Awards Engine + Academic Year FK. | 3d |
| 149 | Medium | State-level consolidated dashboard/report New StateAdmin controller + Vue page; FRD marks this optional. | 4d |
| 150 | Medium | Correction/resubmission loop Rejected → school edits → re-submitted without losing history. | 2d |
| 151 | Medium | Topper "Congratulations" certificates Reuse existing Certificate/CertificateTemplate engine (entity_type='topper'). | 3d |
| 152 | Medium | Achievement → Awards Engine linkage source_award_id FK; auto-populate system-generated achievements. | 2d |
| 153 | Low | Validation hardening pass_count <= total_appeared; prevent duplicate rank within scope. | 1d |
| 154 | Low | Remove/wire dead subject_stats column Currently unused — remove or wire into subject normalization. | 0.5d |
| 155 | Low | Expose Achievement category/level scopes in UI scopeByCategory/scopeByLevel exist but are unused dead code. | 0.5d |
| 156 | Low | Achievement category/level master data Replace inconsistent free-text values with a lookup table/enum. | 1d |
| 157 | Low | Academic_year column on achievements Currently absent — needed to filter/report by year. | 0.5d |